## Tasks
Task ID | Version | Phase | Task | Owner | Start | Finish | Duration (days) | Status | Pct Complete | Milestone | Depends On | Notes
V1-01 | Version 1 | 1. Data Validation | Full 10-yr panel build & dry-run | Data Scientist | 2026-09-16 | 2026-09-26 | 11 | Done | 100% | No
V1-02 | Version 1 | 1. Data Validation | AWP schema exploration | Data Scientist | 2026-09-16 | 2026-10-01 | 16 | Done | 100% | No
V1-03 | Version 1 | 1. Data Validation | Sanity check across years | Data Scientist | 2026-09-26 | 2026-10-01 | 6 | Done | 100% | No | V1-01
V1-04 | Version 1 | 1. Data Validation | Segment-key (ORIGKEY) stability check | Data Scientist | 2026-09-26 | 2026-10-01 | 6 | Done | 100% | No | V1-01
V1-05 | Version 1 | Buffer | Buffer: competing priorities / IT scheduling | Data Scientist | 2026-10-01 | 2026-10-11 | 11 | In progress | 10% | No
V1-06 | Version 1 | 3. Model Refinement | Refit deterioration curve (longitudinal) | Data Scientist | 2026-10-01 | 2026-10-11 | 11 | In progress | 15% | No | V1-03
V1-07 | Version 1 | 2. Cost Integration | AWP-to-PMIS join design & build | Data Scientist | 2026-10-11 | 2026-11-10 | 31 | Not started | 0% | No | V1-04
V1-08 | Version 1 | 3. Model Refinement | Calibrate triggers with pavement engineers | Data Scientist, Pavement Engineers | 2026-10-11 | 2026-10-31 | 21 | Not started | 0% | No | V1-06
V1-09 | Version 1 | 3. Model Refinement | User-cost scope decision | Manager | 2026-10-31 | 2026-10-31 | 1 | Not started | 0% | Yes | V1-08
V1-10 | Version 1 | 2. Cost Integration | Derive real unit costs by treatment | Data Scientist | 2026-11-10 | 2026-11-25 | 16 | Not started | 0% | No | V1-07
V1-11 | Version 1 | 2. Cost Integration | NHCCI cost escalation layer | Data Scientist | 2026-11-25 | 2026-12-02 | 8 | Not started | 0% | No | V1-10
V1-12 | Version 1 | 2. Cost Integration | Rebuild star schema with real costs | Data Scientist | 2026-12-02 | 2026-12-09 | 8 | Not started | 0% | No | V1-11
V1-13 | Version 1 | Buffer | Buffer: cost data validation / rework | Data Scientist | 2026-12-09 | 2026-12-24 | 16 | Not started | 0% | No
V1-14 | Version 1 | 4. Power BI Build | Connect Desktop, relationships, DAX | Data Scientist | 2026-12-24 | 2027-01-08 | 16 | Not started | 0% | No | V1-12
V1-15 | Version 1 | 4. Power BI Build | Report pages + What-If parameters | Data Scientist | 2027-01-08 | 2027-01-20 | 13 | Not started | 0% | No | V1-14
V1-16 | Version 1 | 4. Power BI Build | Gateway + scheduled refresh setup | Data Scientist | 2027-01-20 | 2027-02-01 | 13 | Not started | 0% | No | V1-15
V1-17 | Version 1 | 5. Review & Rollout | Internal engineer review | Data Scientist, Pavement Engineers | 2027-02-01 | 2027-02-16 | 16 | Not started | 0% | No | V1-16
V1-18 | Version 1 | 5. Review & Rollout | Leadership presentation & feedback | Manager, Data Scientist | 2027-02-16 | 2027-03-03 | 16 | Not started | 0% | No | V1-17
V1-19 | Version 1 | 5. Review & Rollout | Documentation & handoff | Data Scientist | 2027-03-03 | 2027-03-13 | 11 | Not started | 0% | No | V1-18
V1-20 | Version 1 | 5. Review & Rollout | Version 1 complete | Data Scientist | 2027-03-13 | 2027-03-13 | 1 | Not started | 0% | Yes | V1-19
V2-01 | Version 2 | 6. Bid Item Analysis | V2 scope & priorities with manager | Manager, Data Scientist | 2027-03-15 | 2027-03-19 | 5 | Not started | 0% | No | V1-20
V2-02 | Version 2 | 6. Bid Item Analysis | Treatment data source & AWP link (incl. HPTL) | Manager | 2027-03-15 | 2027-03-26 | 12 | Not started | 0% | No |  | Treatment type is not stored in AWP
V2-03 | Version 2 | 6. Bid Item Analysis | Inflation index table from PDFs | Intern | 2027-03-15 | 2027-04-02 | 19 | Not started | 0% | No
V2-04 | Version 2 | 6. Bid Item Analysis | Bid item quantity & trend views (Oracle) | Data Scientist | 2027-03-22 | 2027-04-02 | 12 | Not started | 0% | No | V2-01
V2-05 | Version 2 | 6. Bid Item Analysis | Quantity by treatment chart (manager's analysis) | Data Scientist | 2027-04-05 | 2027-04-16 | 12 | Not started | 0% | No | V2-02, V2-04
V2-06 | Version 2 | 6. Bid Item Analysis | Polynomial trend fit (method agreed) | Data Scientist | 2027-04-05 | 2027-04-16 | 12 | Not started | 0% | No | V2-04
V2-07 | Version 2 | 6. Bid Item Analysis | Compare inflation index with NHCCI layer | Data Scientist, Intern | 2027-04-05 | 2027-04-09 | 5 | Not started | 0% | No | V2-03, V1-11
V2-08 | Version 2 | 6. Bid Item Analysis | Validate V2 outputs vs published bid tabs | Intern | 2027-04-12 | 2027-04-23 | 12 | Not started | 0% | No | V2-05
V2-09 | Version 2 | 6. Bid Item Analysis | Review & handoff Version 2 | Manager, Data Scientist | 2027-04-26 | 2027-05-07 | 12 | Not started | 0% | No | V2-08
V2-10 | Version 2 | 6. Bid Item Analysis | Version 2 complete | Data Scientist | 2027-05-07 | 2027-05-07 | 1 | Not started | 0% | Yes | V2-09

## Guide
How to update this task list
Edit | Cells in blue text on the Tasks sheet. Duration is calculated from Start and Finish.
Status | Not started, In progress, Done, or Blocked (dropdown).
Pct Complete | 0% to 100%. The Gantt bar fills in to show progress.
Milestone | Yes shows a diamond on the Gantt chart. Use the same date for Start and Finish.
Phase | Choose from the dropdown so colors match the Gantt legend. To add a phase, also add it to the color list in the Deneb spec.
Adding a task | Type in the first empty row below the table; the table expands automatically. Use the next Task ID (V1-21, V2-11).
New requests | Requests that arrive during Version 1 are added as Version 2 tasks, so Version 1 dates stay unchanged.
Refresh | Save this file, then click Refresh in Power BI.
Assumptions | Status and percent complete reflect progress as of October 2, 2026. Version 2 dates are planning estimates to confirm in task V2-01.