## Timeline
Task | Phase | Start | Finish | Milestone | FinishDate | ColorKey | Version | Owner
Full 10-yr panel build & dry-run | 1. Data Validation | 2026-09-16 | 2026-09-26 | 0 | 2026-09-26 | 1. Data Validation | Version 1 | Data Scientist
AWP schema exploration | 1. Data Validation | 2026-09-16 | 2026-10-01 | 0 | 2026-10-01 | 1. Data Validation | Version 1 | Data Scientist
Sanity check across years | 1. Data Validation | 2026-09-26 | 2026-10-01 | 0 | 2026-10-01 | 1. Data Validation | Version 1 | Data Scientist
Segment-key (ORIGKEY) stability check | 1. Data Validation | 2026-09-26 | 2026-10-01 | 0 | 2026-10-01 | 1. Data Validation | Version 1 | Data Scientist
Buffer: competing priorities / IT scheduling | Buffer | 2026-10-01 | 2026-10-11 | 0 | 2026-10-11 | Buffer | Version 1 | Data Scientist
AWP-to-PMIS join design & build | 2. Cost Integration | 2026-10-11 | 2026-11-10 | 0 | 2026-11-10 | 2. Cost Integration | Version 1 | Data Scientist
Derive real unit costs by treatment | 2. Cost Integration | 2026-11-10 | 2026-11-25 | 0 | 2026-11-25 | 2. Cost Integration | Version 1 | Data Scientist
NHCCI cost escalation layer | 2. Cost Integration | 2026-11-25 | 2026-12-02 | 0 | 2026-12-02 | 2. Cost Integration | Version 1 | Data Scientist
Rebuild star schema with real costs | 2. Cost Integration | 2026-12-02 | 2026-12-09 | 0 | 2026-12-09 | 2. Cost Integration | Version 1 | Data Scientist
Buffer: cost data validation / rework | Buffer | 2026-12-09 | 2026-12-24 | 0 | 2026-12-24 | Buffer | Version 1 | Data Scientist
Refit deterioration curve (longitudinal) | 3. Model Refinement | 2026-10-01 | 2026-10-11 | 0 | 2026-10-11 | 3. Model Refinement | Version 1 | Data Scientist
Calibrate triggers with pavement engineers | 3. Model Refinement | 2026-10-11 | 2026-10-31 | 0 | 2026-10-31 | 3. Model Refinement | Version 1 | Data Scientist, Pavement Engineers
User-cost scope decision | 3. Model Refinement | 2026-10-31 | 2026-10-31 | 1 | 2026-11-02 | Milestone | Version 1 | Manager
Connect Desktop, relationships, DAX | 4. Power BI Build | 2026-12-24 | 2027-01-08 | 0 | 2027-01-08 | 4. Power BI Build | Version 1 | Data Scientist
Report pages + What-If parameters | 4. Power BI Build | 2027-01-08 | 2027-01-20 | 0 | 2027-01-20 | 4. Power BI Build | Version 1 | Data Scientist
Gateway + scheduled refresh setup | 4. Power BI Build | 2027-01-20 | 2027-02-01 | 0 | 2027-02-01 | 4. Power BI Build | Version 1 | Data Scientist
Internal engineer review | 5. Review & Rollout | 2027-02-01 | 2027-02-16 | 0 | 2027-02-16 | 5. Review & Rollout | Version 1 | Data Scientist
Leadership presentation & feedback | 5. Review & Rollout | 2027-02-16 | 2027-03-03 | 0 | 2027-03-03 | 5. Review & Rollout | Version 1 | Manager, Data Scientist
Documentation & handoff | 5. Review & Rollout | 2027-03-03 | 2027-03-13 | 0 | 2027-03-13 | 5. Review & Rollout | Version 1 | Data Scientist
Version 1 complete | 5. Review & Rollout | 2027-03-13 | 2027-03-13 | 1 | 2027-03-15 | Milestone | Version 1 | Data Scientist
V2 scope & priorities with manager | 6. Version 2: Bid Item Analysis | 2027-03-15 | 2027-03-19 | 0 | 2027-03-19 | 6. Version 2: Bid Item Analysis | Version 2 | Manager, Data Scientist
Treatment data source & AWP link (incl. HPTL) | 6. Version 2: Bid Item Analysis | 2027-03-15 | 2027-03-26 | 0 | 2027-03-26 | 6. Version 2: Bid Item Analysis | Version 2 | Manager
Inflation index table from PDFs | 6. Version 2: Bid Item Analysis | 2027-03-15 | 2027-04-02 | 0 | 2027-04-02 | 6. Version 2: Bid Item Analysis | Version 2 | Intern
Bid item quantity & trend views (Oracle) | 6. Version 2: Bid Item Analysis | 2027-03-22 | 2027-04-02 | 0 | 2027-04-02 | 6. Version 2: Bid Item Analysis | Version 2 | Data Scientist
Quantity by treatment chart (manager's analysis) | 6. Version 2: Bid Item Analysis | 2027-04-05 | 2027-04-16 | 0 | 2027-04-16 | 6. Version 2: Bid Item Analysis | Version 2 | Data Scientist
Polynomial trend fit (method agreed) | 6. Version 2: Bid Item Analysis | 2027-04-05 | 2027-04-16 | 0 | 2027-04-16 | 6. Version 2: Bid Item Analysis | Version 2 | Data Scientist
Compare inflation index with NHCCI layer | 6. Version 2: Bid Item Analysis | 2027-04-05 | 2027-04-09 | 0 | 2027-04-09 | 6. Version 2: Bid Item Analysis | Version 2 | Data Scientist
Validate V2 outputs vs published bid tabs | 6. Version 2: Bid Item Analysis | 2027-04-12 | 2027-04-23 | 0 | 2027-04-23 | 6. Version 2: Bid Item Analysis | Version 2 | Intern
Review & handoff Version 2 | 6. Version 2: Bid Item Analysis | 2027-04-26 | 2027-05-07 | 0 | 2027-05-07 | 6. Version 2: Bid Item Analysis | Version 2 | Manager, Data Scientist
Version 2 complete | 6. Version 2: Bid Item Analysis | 2027-05-07 | 2027-05-07 | 1 | 2027-05-09 | Milestone | Version 2 | Data Scientist