## Tasks
Task ID | Version | Workstream | Phase | Task | Owner | Start | End | Duration (days) | Status | Depends On | Milestone
V1-01 | Version 1 | A. Database & Power BI | Access & discovery | Request Oracle permissions from IT | Data Scientist | 2026-10-05 | 2026-10-09 | 5 | In progress |  | No
V1-02 | Version 1 | A. Database & Power BI | Access & discovery | Send scope recap | Data Scientist | 2026-10-09 | 2026-10-09 | 1 | Not started |  | Yes
V1-03 | Version 1 | A. Database & Power BI | Access & discovery | List tables, columns, and keys from Oracle catalog | Data Scientist | 2026-10-07 | 2026-10-14 | 8 | Not started | V1-01 | No
V1-04 | Version 1 | A. Database & Power BI | Access & discovery | Identify core bid tables | Data Scientist | 2026-10-12 | 2026-10-16 | 5 | Not started | V1-03 | No
V1-05 | Version 1 | A. Database & Power BI | Data dictionary | Export catalog and profile key fields | Data Scientist | 2026-10-12 | 2026-10-23 | 12 | Not started | V1-03 | No
V1-06 | Version 1 | A. Database & Power BI | Data dictionary | Draft descriptions; send questions to Contract Office | Data Scientist | 2026-10-19 | 2026-10-30 | 12 | Not started | V1-05 | No
V1-07 | Version 1 | A. Database & Power BI | Data dictionary | Data dictionary draft | Data Scientist | 2026-10-30 | 2026-10-30 | 1 | Not started | V1-06 | Yes
V1-08 | Version 1 | A. Database & Power BI | Oracle views | Build joins with row-count checks | Data Scientist | 2026-10-19 | 2026-10-30 | 12 | Not started | V1-04 | No
V1-09 | Version 1 | A. Database & Power BI | Oracle views | Check item code and unit consistency across years | Data Scientist | 2026-10-26 | 2026-11-04 | 10 | Not started | V1-08 | No
V1-10 | Version 1 | A. Database & Power BI | Oracle views | Create detail view (v_bid_item_detail) | Data Scientist | 2026-11-02 | 2026-11-06 | 5 | Not started | V1-08 | No
V1-11 | Version 1 | A. Database & Power BI | Oracle views | Create trend view (v_bid_item_qty_trend) | Data Scientist | 2026-11-04 | 2026-11-10 | 7 | Not started | V1-10 | No
V1-12 | Version 1 | C. Validation & testing | Validation | Reconcile 3 lettings against published bid tabs | Intern | 2026-11-02 | 2026-11-13 | 12 | Not started | V1-10 | No
V1-13 | Version 1 | A. Database & Power BI | Validation | Views built and validated | Data Scientist | 2026-11-13 | 2026-11-13 | 1 | Not started | V1-11, V1-12 | Yes
V1-14 | Version 1 | A. Database & Power BI | Power BI | Connect to views; build data model, Date and Items tables | Data Scientist | 2026-11-16 | 2026-11-20 | 5 | Not started | V1-13 | No
V1-15 | Version 1 | A. Database & Power BI | Power BI | Build measures and quantity trend page | Data Scientist | 2026-11-18 | 2026-12-02 | 15 | Not started | V1-14 | No
V1-16 | Version 1 | C. Validation & testing | Power BI | Test report and log issues | Intern | 2026-11-30 | 2026-12-04 | 5 | Not started | V1-15 | No
V1-17 | Version 1 | A. Database & Power BI | Power BI | Power BI first draft | Data Scientist | 2026-12-04 | 2026-12-04 | 1 | Not started | V1-15 | Yes
V1-18 | Version 1 | A. Database & Power BI | Review & handover | Review draft with manager and apply changes | Data Scientist | 2026-12-07 | 2026-12-11 | 5 | Not started | V1-17 | No
V1-19 | Version 1 | A. Database & Power BI | Review & handover | Finalize data dictionary and user guide | Data Scientist | 2026-12-09 | 2026-12-16 | 8 | Not started | V1-18 | No
V1-20 | Version 1 | A. Database & Power BI | Review & handover | Version 1 complete | Data Scientist | 2026-12-18 | 2026-12-18 | 1 | Not started | V1-19 | Yes
V2-01 | Version 2 | A. Database & Power BI | Planning | Agree Version 2 scope and priorities | Manager | 2027-01-04 | 2027-01-08 | 5 | Not started | V1-20 | No
V2-02 | Version 2 | B. Inflation index | Inflation index | Collect inflation index table (year, quarter, index, source) | Intern | 2027-01-04 | 2027-01-29 | 26 | Not started |  | No
V2-03 | Version 2 | B. Treatment data | Treatment data | Identify treatment data source and link key to AWP | Manager | 2027-01-04 | 2027-01-22 | 19 | Not started |  | No
V2-04 | Version 2 | A. Database & Power BI | Oracle views | Join inflation index; add inflation-adjusted prices | Data Scientist | 2027-02-01 | 2027-02-12 | 12 | Not started | V2-02 | No
V2-05 | Version 2 | A. Database & Power BI | Oracle views | Link treatment data to bid items | Data Scientist | 2027-02-01 | 2027-02-19 | 19 | Not started | V2-03 | No
V2-06 | Version 2 | A. Database & Power BI | Power BI | Quantity by treatment page (manager's chart) | Data Scientist | 2027-02-15 | 2027-03-05 | 19 | Not started | V2-05 | No
V2-07 | Version 2 | A. Database & Power BI | Power BI | Agree polynomial method; build trend fit | Data Scientist | 2027-02-22 | 2027-03-05 | 12 | Not started | V2-01 | No
V2-08 | Version 2 | A. Database & Power BI | Power BI | Unit price trends and bid competition page | Data Scientist | 2027-03-01 | 2027-03-19 | 19 | Not started | V2-04 | No
V2-09 | Version 2 | A. Database & Power BI | Modeling | Bid price prediction model | Data Scientist | 2027-03-01 | 2027-04-16 | 47 | Not started | V2-04 | No
V2-10 | Version 2 | C. Validation & testing | Validation | Validate and test Version 2 additions | Intern | 2027-04-05 | 2027-04-16 | 12 | Not started | V2-06, V2-08 | No
V2-11 | Version 2 | A. Database & Power BI | Review & handover | Review with manager and finalize | Data Scientist | 2027-04-19 | 2027-04-28 | 10 | Not started | V2-10 | No
V2-12 | Version 2 | A. Database & Power BI | Review & handover | Version 2 complete | Data Scientist | 2027-04-30 | 2027-04-30 | 1 | Not started | V2-11 | Yes

## Guide
How to use this task list
What to edit | All columns in blue text on the Tasks sheet. Duration is calculated automatically.
Status | Choose from the dropdown: Not started, In progress, Done, Blocked. The Gantt chart colors bars by status.
Milestone | Yes shows a diamond on the Gantt chart instead of a bar. Use the same date for Start and End.
Adding a task | Type in the first empty row below the table; the table expands automatically. Keep the Task ID format (V1-21, V2-13) so tasks sort in order.
Version 2 requests | New requests during Version 1 go in as Version 2 tasks, so the Version 1 dates stay unchanged.
Power BI | Load the ProjectTasks table into Power BI, then add all columns to the Deneb visual as described in the Deneb setup guide.
Assumptions | Version 2 dates (January to April 2027) are planning estimates and will be confirmed in the Version 2 scope meeting (task V2-01).