## Timeline
Task | Phase | Start | Finish | Milestone | FinishDate | ColorKey
Full 10-yr panel build & dry-run | 1. Data Validation | 2026-09-16 | 2026-09-26 | 0 | 2026-09-26 | 1. Data Validation
AWP schema exploration | 1. Data Validation | 2026-09-16 | 2026-10-01 | 0 | 2026-10-01 | 1. Data Validation
Sanity check across years | 1. Data Validation | 2026-09-26 | 2026-10-01 | 0 | 2026-10-01 | 1. Data Validation
Segment-key (ORIGKEY) stability check | 1. Data Validation | 2026-09-26 | 2026-10-01 | 0 | 2026-10-01 | 1. Data Validation
Buffer: competing priorities / IT scheduling | Buffer | 2026-10-01 | 2026-10-11 | 0 | 2026-10-11 | Buffer
AWP-to-PMIS join design & build | 2. Cost Integration | 2026-10-11 | 2026-11-10 | 0 | 2026-11-10 | 2. Cost Integration
Derive real unit costs by treatment | 2. Cost Integration | 2026-11-10 | 2026-11-25 | 0 | 2026-11-25 | 2. Cost Integration
NHCCI cost escalation layer | 2. Cost Integration | 2026-11-25 | 2026-12-02 | 0 | 2026-12-02 | 2. Cost Integration
Rebuild star schema with real costs | 2. Cost Integration | 2026-12-02 | 2026-12-09 | 0 | 2026-12-09 | 2. Cost Integration
Buffer: cost data validation / rework | Buffer | 2026-12-09 | 2026-12-24 | 0 | 2026-12-24 | Buffer
Refit deterioration curve (longitudinal) | 3. Model Refinement | 2026-10-01 | 2026-10-11 | 0 | 2026-10-11 | 3. Model Refinement
Calibrate triggers with pavement engineers | 3. Model Refinement | 2026-10-11 | 2026-10-31 | 0 | 2026-10-31 | 3. Model Refinement
User-cost scope decision | 3. Model Refinement | 2026-10-31 | 2026-10-31 | 1 | 2026-11-02 | Milestone
Connect Desktop, relationships, DAX | 4. Power BI Build | 2026-12-24 | 2027-01-08 | 0 | 2027-01-08 | 4. Power BI Build
Report pages + What-If parameters | 4. Power BI Build | 2027-01-08 | 2027-01-20 | 0 | 2027-01-20 | 4. Power BI Build
Gateway + scheduled refresh setup | 4. Power BI Build | 2027-01-20 | 2027-02-01 | 0 | 2027-02-01 | 4. Power BI Build
Internal engineer review | 5. Review & Rollout | 2027-02-01 | 2027-02-16 | 0 | 2027-02-16 | 5. Review & Rollout
Leadership presentation & feedback | 5. Review & Rollout | 2027-02-16 | 2027-03-03 | 0 | 2027-03-03 | 5. Review & Rollout
Documentation & handoff | 5. Review & Rollout | 2027-03-03 | 2027-03-13 | 0 | 2027-03-13 | 5. Review & Rollout